## Actual cost
Activity ID | Activity Name | Total | 1-Feb-22 | 8-Feb-22 | 15-Feb-22 | 22-Feb-22 | 1-Mar-22 | 8-Mar-22 | 15-Mar-22 | 22-Mar-22 | 29-Mar-22 | 5-Apr-22 | 12-Apr-22 | 19-Apr-22 | 26-Apr-22 | 3-May-22 | 10-May-22 | 17-May-22 | 24-May-22 | 31-May-22 | 7-Jun-22 | 14-Jun-22 | 21-Jun-22 | 28-Jun-22 | 5-Jul-22 | 12-Jul-22 | 19-Jul-22
A1050 | Civil Works | 2500 | 2500
A1060 | Waterproofing/Anti-Termite | 800 | 666.67 | 133.33
A1070 | Lean Concrete | 2200 |  | 2200
0
A1080 | Foundation (Rebar, Formwork, Concrete) | 12000 |  | 1770.49 | 10229.51
A1090 | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | 13500 |  |  |  | 7256.25 | 6243.75
A1100 | Slabs, beams, staircases concrete 1 Floor | 16000 | [5 empty] | 11428.57 | 4571.43
A1110 | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | 17000.01 | [6 empty] | 1593.75 | 6906.25 | 5046.88 | 3453.13
A1120 | Slabs, beams 2 Floor | 500 | [9 empty] | 500
A1130 | Masonry Works | 2499.99 | [7 empty] | 833.33 | 989.58 | 677.08
0
A1140 | Roof Steel Structure | 0
A1150 | Middle Frames Installation | 0
A1160 | Installation of Metal Sheets | 0
A1170 | Waterproofing | 0
A1180 | Clay Tiles | 0
A1190 | Terrace Heat Insulation | 217.49 | [8 empty] | 190.3 | 27.19
A1200 | Terraces Sloped Screed | 434.96 | [9 empty] | 434.96
A1210 | Terraces Waterproofing | 425 | [9 empty] | 425
A1220 | Finishing | 0
A1230 | Sub Frame for Windows | 0
A1240 | Windows & Doors | 0
A1250 | Curtain Wall | 0
A1260 | Sliding Doors | 0
A1270 | EPS Fixing | 0
A1280 | Plaster for Walls | 0
A1290 | Stone | 0
A1300 | Decorative Plaster | 0
A1310 | Shutters&Louvers | 0
A1320 | Exterior Balustrades | 0
A1330 | Framing for Gypsum Walls | 0
A1340 | Gypsum Board Lining for Walls | 0
A1350 | Framing of Suspended Ceilings | 0
A1360 | Gypsum Board Lining for Ceiling | 0
A1370 | Heat Insulation for Interiors | 0
0
A1380 | Screed for Interiors | 0
A1390 | Waterproofing for Wet Areas | 0
A1400 | Interior Steel Installation | 0
A1410 | Stone Wall Cladding | 0
A1420 | Timber Wall Covering | 0
A1430 | Paint for Wall | 0
A1440 | Wall Covering & Upholstery | 0
A1450 | Paint for Ceiling | 0
A1460 | Stone Flooring | 0
A1470 | Parquet Flooring | 0
A1480 | Stair Cladding | 0
A1490 | Internal Doors Installations | 0
A1500 | Kitchen | 0
A1510 | Sanitary Installations | 0
A1520 | Joinery Installations | 0
A1530 | FF&E | 0
A1540 | Interior Balustrade | 0
A1550 | Initial Piping Works Below Ground Level | 4871.6 |  | 718.76 | 4152.84
A1560 | Steel Pipes & Steel Works | 10439.15 |  | 782.94 | 4523.63 | 4523.63 | 608.95
A1570 | Internal Plumbing | 0
A1580 | Ductwork & Dampers | 0
A1590 | Cable Trays | 0
A1600 | Conduits | 0
A1610 | Earthing & Lightning Protection | 0
A1620 | Cables | 0
A1630 | Fan coil & Silencers & Flexible Ducts | 0
A1640 | Strainers & Grills | 0
A1650 | Insulation | 0
A1660 | Underfloor Heating System | 0
A1670 | Sprinkler | 0
A1680 | Embedded Lightning Fixtures | 0
A1690 | Fire Hose Cabinets | 0
A1700 | Slot Diffusers | 0
A1710 | Switches & Sockets & Outlets | 0
A1720 | ELV Equipment Installation | 0
A1730 | Roof Lighting Protection | 0
A1740 | Cabinets&Panels | 0

## File Credit (hidden)
Credit & Author: Sama Tamhidi
khonamon.com