## Planned Cost
Activity ID | WBS | Activity Name | Subcontractor | Total | 1-Feb-22 | 8-Feb-22 | 15-Feb-22 | 22-Feb-22 | 1-Mar-22 | 8-Mar-22 | 15-Mar-22 | 22-Mar-22 | 29-Mar-22 | 5-Apr-22 | 12-Apr-22 | 19-Apr-22 | 26-Apr-22 | 3-May-22 | 10-May-22 | 17-May-22 | 24-May-22 | 31-May-22 | 7-Jun-22 | 14-Jun-22 | 21-Jun-22 | 28-Jun-22 | 5-Jul-22 | 12-Jul-22 | 19-Jul-22
A1050 | Structural Works | Civil Works | Khonamon | 2500 | 2500
A1060 | Structural Works | Waterproofing/Anti-Termite | Khonamon | 800 | 666.67 | 133.33
0
A1070 | Structural Works | Lean Concrete | Khonamon | 2200 |  | 2200
A1080 | Structural Works | Foundation (Rebar, Formwork, Concrete) | Khonamon | 12300 |  | 5271.43 | 7028.57
Planned
A1090 | Structural Works | Columns & walls concrete (Rebar, Formwork, Concrete) 1 Floor | Khonamon | 14500 |  |  | 725 | 9425 | 4350
A1100 | Structural Works | Slabs, beams, staircases concrete 1 Floor | Khonamon | 15500 | [5 empty] | 11071.43 | 4428.57
0
A1110 | Structural Works | Columns and walls concrete (Rebar, Formwork, Concrete) 2 Floor | Khonamon | 16500 | [6 empty] | 2475 | 10725 | 3300
A1120 | Structural Works | Slabs, beams 2 Floor | Khonamon | 17500 | [9 empty] | 8263.89 | 9236.11
A1130 | Masonry Works | Masonry Works | Khonamon | 5500 | [7 empty] | 1222.22 | 1451.39 | 1986.11 | 840.28
A1140 | Roof | Roof Steel Structure | Khonamon | 4500 | [12 empty] | 3696.43 | 803.57
A1150 | Roof | Middle Frames Installation | Khonamon | 950 | [13 empty] | 950
A1160 | Roof | Installation of Metal Sheets | Khonamon | 4700 | [13 empty] | 4700
A1170 | Roof | Waterproofing | Khonamon | 1400 | [13 empty] | 875 | 525
A1180 | Roof | Clay Tiles | Khonamon | 2800 | [14 empty] | 2800
A1190 | Terraces | Terrace Heat Insulation | Pemax | 217.49 | [8 empty] | 190.3 | 27.19
0
A1200 | Terraces | Terraces Sloped Screed | Pemax | 434.96 | [9 empty] | 434.96
A1210 | Terraces | Terraces Waterproofing | Pemax | 855.43 | [9 empty] | 855.43
A1220 | Terraces | Finishing | Pemax | 2174.82 | [14 empty] | 2066.08 | 108.74
A1230 | Façade | Sub Frame for Windows | Pemax | 3131.75 | [12 empty] | 2125.12 | 1006.63
A1240 | Façade | Windows & Doors | Pemax | 11599.06 | [13 empty] | 3521.14 | 5385.28 | 2692.64
A1250 | Façade | Curtain Wall | Pemax | 11599.06 | [13 empty] | 4929.6 | 6669.46
A1260 | Façade | Sliding Doors | Pemax | 11599.06 | [13 empty] | 3521.14 | 5385.28 | 2692.64
A1270 | Façade | EPS Fixing | Pemax | 1667.37 | [12 empty] | 1131.43 | 535.94
A1280 | Façade | Plaster for Walls | Pemax | 2218.32 | [13 empty] | 1571.31 | 647.01
0
A1290 | Façade | Stone | Pemax | 7524.89 | [14 empty] | 2553.09 | 3493.7 | 1478.1
A1300 | Façade | Decorative Plaster | Pemax | 2551.79 | [16 empty] | 2392.3 | 159.49
A1310 | Façade | Shutters&Louvers | Pemax | 130.49 | [15 empty] | 60.58 | 69.91
A1320 | Façade | Exterior Balustrades | Pemax | 8684.8 | [21 empty] | 7754.29 | 930.51
A1330 | Fit-out | Framing for Gypsum Walls | Pemax | 7466.9 | [12 empty] | 2533.41 | 3466.78 | 1466.71
A1340 | Fit-out | Gypsum Board Lining for Walls | Pemax | 5973.51 | [15 empty] | 186.67 | 4853.48 | 933.36
A1350 | Fit-out | Framing of Suspended Ceilings | Pemax | 1826.85 | [17 empty] | 1370.14 | 456.71
A1360 | Fit-out | Gypsum Board Lining for Ceiling | Pemax | 1826.85 | [19 empty] | 742.16 | 1084.69
A1370 | Fit-out | Heat Insulation for Interiors | Pemax | 637.95 | [17 empty] | 637.95
0
A1380 | Fit-out | Screed for Interiors | Pemax | 1783.36 | [17 empty] | 1783.36
A1390 | Fit-out | Waterproofing for Wet Areas | Pemax | 855.43 | [17 empty] | 71.29 | 784.14
A1400 | Fit-out | Interior Steel Installation | Pemax | 7959.86 | [12 empty] | 7959.86
A1410 | Finishing | Stone Wall Cladding | Pemax | 17529.08 | [18 empty] | 6573.41 | 10955.67
A1420 | Finishing | Timber Wall Covering | Pemax | 5727.05 | [19 empty] | 143.18 | 3722.58 | 1861.29
A1430 | Finishing | Paint for Wall | Pemax | 869.93 | [21 empty] | 706.82 | 163.11
A1440 | Finishing | Wall Covering & Upholstery | Pemax | 1159.91 | [22 empty] | 1159.91
A1450 | Finishing | Paint for Ceiling | Pemax | 1304.89 | [21 empty] | 1060.22 | 244.67
A1460 | Finishing | Stone Flooring | Pemax | 19906.89 | [19 empty] | 710.96 | 18484.97 | 710.96
A1470 | Finishing | Parquet Flooring | Pemax | 536.46 | [21 empty] | 478.98 | 57.48
A1480 | Finishing | Stair Cladding | Pemax | 1200 | [12 empty] | 660 | 540
A1490 | Finishing | Internal Doors Installations | Pemax | 3653.7 | [22 empty] | 3001.25 | 652.45
A1500 | Finishing | Kitchen | Pemax | 724.95 | [20 empty] | 543.71 | 181.24
A1510 | Finishing | Sanitary Installations | Pemax | 1391.89 | [21 empty] | 1391.89
A1520 | Finishing | Joinery Installations | Pemax | 9134.26 | [22 empty] | 9134.26
A1530 | Finishing | FF&E | Pemax | 1449.88 | [22 empty] | 362.47 | 1087.41
A1540 | Finishing | Interior Balustrade | Pemax | 2609.79 | [13 empty] | 2218.32 | 391.47
A1550 | MEP | Initial Piping Works Below Ground Level | Pemax | 4871.6 |  | 2087.83 | 2783.77
A1560 | MEP | Steel Pipes & Steel Works | Pemax | 10439.15 |  | 2087.83 | 4523.63 | 3827.69
0
A1570 | MEP | Internal Plumbing | Pemax | 6959.44 | [14 empty] | 2609.79 | 4349.65
A1580 | MEP | Ductwork & Dampers | Pemax | 10439.15 | [14 empty] | 2609.79 | 4523.63 | 3305.73
A1590 | MEP | Cable Trays | Pemax | 2029.84 | [16 empty] | 761.19 | 1268.65
A1600 | MEP | Conduits | Pemax | 7104.42 | [17 empty] | 5328.31 | 1776.11
A1610 | MEP | Earthing & Lightning Protection | Pemax | 1014.92 | [14 empty] | 1014.92
A1620 | MEP | Cables | Pemax | 7104.42 | [18 empty] | 4820.86 | 2283.56
A1630 | MEP | Fan coil & Silencers & Flexible Ducts | Pemax | 3479.72 | [16 empty] | 1217.9 | 2261.82
A1640 | MEP | Strainers & Grills | Pemax | 4871.61 | [17 empty] | 2261.82 | 2609.79
A1650 | MEP | Insulation | Pemax | 4871.61 | [9 empty] | 2261.82 | 2609.79
A1660 | MEP | Underfloor Heating System | Pemax | 4871.62 | [17 empty] | 173.99 | 4523.64 | 173.99
A1670 | MEP | Sprinkler | Pemax | 2100 | [19 empty] | 2100
A1680 | MEP | Embedded Lightning Fixtures | Pemax | 3044.75 | [17 empty] | 3044.75
A1690 | MEP | Fire Hose Cabinets | Pemax | 1391.89 | [21 empty] | 1391.89
A1700 | MEP | Slot Diffusers | Pemax | 2783.77 | [22 empty] | 2783.77
A1710 | MEP | Switches & Sockets & Outlets | Pemax | 5074.59 | [23 empty] | 5074.59
A1720 | MEP | ELV Equipment Installation | Pemax | 5074.59 | [23 empty] | 253.73 | 4820.86
A1730 | MEP | Roof Lighting Protection | Pemax | 3044.75 | [16 empty] | 3044.75
A1740 | MEP | Cabinets&Panels | Pemax | 7104.42 | [22 empty] | 761.19 | 6343.23

## File Credit (hidden)
Credit & Author: Sama Tamhidi
khonamon.com